## Read me
PPM compliance report template (planned vs completed, by site)
From IVP.ai · ivp.ai/templates/ppm-compliance-report-template
THE SAMPLE ROWS IN THIS WORKBOOK ARE FICTIONAL. Sites, assets and tasks are invented for illustration. Delete them before you enter your own data.
How to use it
1. Settings: set the period start and end dates, the tolerance (days allowed after the due date) and your RAG thresholds.
2. Sites: list every site on the contract, one row each (site_id must match the Tasks sheet).
3. Tasks: paste one row per PPM task instance due in the period, exported from your job management system. Fill columns A to K only.
Column L (outcome) and M (days late) are formulas. Do not type over them.
4. By site and By asset category recalculate automatically. RAG colours update with the Settings thresholds.
5. Exceptions: on the Tasks sheet, filter column L to anything other than 'On time'. Statutory exceptions (column G = Y) go first in your report.
Definitions
Due in period: task instances whose due date falls between the period start and end. Rows outside the period show 'Out of period' and are not counted.
On time: completed on or before the due date plus the tolerance.
Late: completed, but after the due date plus the tolerance.
No access: the visit was attempted but the task could not be done; record the reason in column K.
Carried over: due in the period and still open when the report is run. It rolls into next period's list as overdue.
Compliance % = On time / Due in period.
Adjusted compliance % = On time / (Due in period - No access). Only use this if your contract allows evidenced no-access to be excluded.
RAG: Red if any statutory task is carried over or adjusted compliance is below the amber threshold; Amber if below the green threshold; otherwise Green.
Thresholds and tolerances in the Settings sheet are examples. Use the figures in your own contract.
Task frequencies and statutory flags should come from your own maintenance task library (for example SFG20, sfg20.co.uk). This template contains no SFG20 content.

## By site
PPM compliance by site
site_id | site_name | Due in period | On time | Late | No access | Carried over | Statutory carried over | Compliance % | Adjusted compliance % | RAG
All

## By asset category
PPM compliance by asset category
Type your asset categories in column A (yellow cells), spelled exactly as on the Tasks sheet.
asset_category | Due in period | On time | Late | No access | Carried over | Statutory carried over | Compliance % | Adjusted compliance % | RAG
Fire alarm
Emergency lighting
Water hygiene
Heating and boilers
Air conditioning
Doors and shutters
All

## Tasks
task_id | site_id | asset_id | asset_category | task_ref | frequency | statutory | due_date | status | completed_date | no_access_reason | outcome | days_late
T0020 | S01 | S01-AC11 | Air conditioning | AC-020 | Quarterly | N | 2026-10-01 | Completed | 2026-10-01
T0011 | S01 | S01-WH08 | Water hygiene | WH-010 | Quarterly | Y | 2026-10-03 | Completed | 2026-10-02
T0009 | S01 | S01-HB04 | Heating and boilers | HB-006 | Annual | N | 2026-10-05 | Completed | 2026-10-02
T0001 | S01 | S01-WH03 | Water hygiene | WH-018 | Quarterly | Y | 2026-10-09 | Completed | 2026-10-09
T0016 | S01 | S01-WH12 | Water hygiene | WH-012 | Monthly | Y | 2026-10-10 | Completed | 2026-10-08
T0004 | S01 | S01-EL01 | Emergency lighting | EL-001 | Monthly | Y | 2026-10-14 | Completed | 2026-10-13
T0015 | S01 | S01-FA04 | Fire alarm | FA-007 | Quarterly | Y | 2026-10-14 | Completed | 2026-10-14
T0010 | S01 | S01-EL08 | Emergency lighting | EL-013 | Monthly | Y | 2026-10-15 | Completed | 2026-10-13
T0014 | S01 | S01-FA01 | Fire alarm | FA-006 | Weekly | Y | 2026-10-17 | Completed | 2026-10-16
T0007 | S01 | S01-EL06 | Emergency lighting | EL-007 | Monthly | Y | 2026-10-18 | Completed | 2026-10-15
T0012 | S01 | S01-DS08 | Doors and shutters | DS-008 | Six-monthly | N | 2026-10-19 | Completed | 2026-10-17
T0013 | S01 | S01-AC08 | Air conditioning | AC-002 | Six-monthly | N | 2026-10-20 | Completed | 2026-10-22
T0003 | S01 | S01-DS10 | Doors and shutters | DS-009 | Six-monthly | N | 2026-10-21 | Completed | 2026-10-18
T0005 | S01 | S01-DS05 | Doors and shutters | DS-017 | Six-monthly | N | 2026-10-22 | Completed | 2026-10-19
T0019 | S01 | S01-AC09 | Air conditioning | AC-008 | Six-monthly | N | 2026-10-22 | Completed | 2026-10-20
T0002 | S01 | S01-EL11 | Emergency lighting | EL-012 | Monthly | Y | 2026-10-24 | Completed | 2026-10-24
T0017 | S01 | S01-WH08 | Water hygiene | WH-010 | Monthly | Y | 2026-10-24 | Completed | 2026-10-22
T0006 | S01 | S01-HB08 | Heating and boilers | HB-017 | Annual | N | 2026-10-26 | Completed | 2026-10-22
T0008 | S01 | S01-DS08 | Doors and shutters | DS-007 | Six-monthly | N | 2026-10-28 | Completed | 2026-10-28
T0018 | S01 | S01-WH03 | Water hygiene | WH-003 | Quarterly | Y | 2026-10-28 | Completed | 2026-10-26
T0032 | S02 | S02-HB03 | Heating and boilers | HB-011 | Quarterly | N | 2026-10-01 | Completed | 2026-10-01
T0036 | S02 | S02-EL09 | Emergency lighting | EL-013 | Monthly | Y | 2026-10-01 | Completed | 2026-10-01
T0030 | S02 | S02-FA06 | Fire alarm | FA-002 | Quarterly | Y | 2026-10-04 | No access |  | Keyholder not present
T0021 | S02 | S02-HB05 | Heating and boilers | HB-016 | Quarterly | N | 2026-10-07 | Completed | 2026-10-04
T0024 | S02 | S02-DS12 | Doors and shutters | DS-019 | Six-monthly | N | 2026-10-07 | Completed | 2026-10-07
T0022 | S02 | S02-HB04 | Heating and boilers | HB-001 | Annual | N | 2026-10-12 | Completed | 2026-10-10
T0031 | S02 | S02-AC10 | Air conditioning | AC-006 | Quarterly | N | 2026-10-12 | Completed | 2026-10-08
T0027 | S02 | S02-HB06 | Heating and boilers | HB-016 | Annual | N | 2026-10-13 | Completed | 2026-10-13
T0026 | S02 | S02-DS06 | Doors and shutters | DS-005 | Six-monthly | N | 2026-10-14 | Completed | 2026-10-19
T0033 | S02 | S02-AC12 | Air conditioning | AC-011 | Six-monthly | N | 2026-10-14 | Completed | 2026-10-11
T0034 | S02 | S02-WH09 | Water hygiene | WH-012 | Monthly | Y | 2026-10-19 | Completed | 2026-10-15
T0037 | S02 | S02-AC10 | Air conditioning | AC-020 | Six-monthly | N | 2026-10-23 | Completed | 2026-10-23
T0035 | S02 | S02-FA02 | Fire alarm | FA-007 | Quarterly | Y | 2026-10-25 | Completed | 2026-10-21
T0038 | S02 | S02-WH05 | Water hygiene | WH-019 | Quarterly | Y | 2026-10-26 | Completed | 2026-10-26
T0028 | S02 | S02-FA08 | Fire alarm | FA-017 | Weekly | Y | 2026-10-28 | Completed | 2026-10-26
T0029 | S02 | S02-DS12 | Doors and shutters | DS-017 | Six-monthly | N | 2026-10-28 | Completed | 2026-10-27
T0023 | S02 | S02-WH03 | Water hygiene | WH-004 | Monthly | Y | 2026-10-29 | Completed | 2026-10-29
T0025 | S02 | S02-EL06 | Emergency lighting | EL-020 | Monthly | Y | 2026-10-31 | Completed | 2026-10-27
T0054 | S03 | S03-DS05 | Doors and shutters | DS-020 | Six-monthly | N | 2026-10-02 | Completed | 2026-10-01
T0044 | S03 | S03-DS05 | Doors and shutters | DS-018 | Six-monthly | N | 2026-10-04 | Completed | 2026-10-04
T0052 | S03 | S03-AC05 | Air conditioning | AC-004 | Six-monthly | N | 2026-10-04 | Completed | 2026-10-02
T0039 | S03 | S03-EL08 | Emergency lighting | EL-017 | Monthly | Y | 2026-10-06 | No access |  | Room in use, client refused access
T0041 | S03 | S03-HB07 | Heating and boilers | HB-001 | Quarterly | N | 2026-10-06 | Completed | 2026-10-02
T0048 | S03 | S03-EL10 | Emergency lighting | EL-017 | Monthly | Y | 2026-10-10 | Completed | 2026-10-09
T0045 | S03 | S03-HB03 | Heating and boilers | HB-011 | Annual | N | 2026-10-15 | Completed | 2026-10-13
T0051 | S03 | S03-AC11 | Air conditioning | AC-020 | Six-monthly | N | 2026-10-15 | Completed | 2026-10-14
T0040 | S03 | S03-HB08 | Heating and boilers | HB-008 | Quarterly | N | 2026-10-17 | Completed | 2026-10-19
T0047 | S03 | S03-FA07 | Fire alarm | FA-009 | Quarterly | Y | 2026-10-17 | Completed | 2026-10-15
T0053 | S03 | S03-EL02 | Emergency lighting | EL-012 | Monthly | Y | 2026-10-17 | Completed | 2026-10-14
T0042 | S03 | S03-EL07 | Emergency lighting | EL-015 | Monthly | Y | 2026-10-19 | Open
T0050 | S03 | S03-DS10 | Doors and shutters | DS-019 | Six-monthly | N | 2026-10-21 | Completed | 2026-10-19
T0049 | S03 | S03-HB11 | Heating and boilers | HB-005 | Quarterly | N | 2026-10-23 | Completed | 2026-10-19
T0046 | S03 | S03-HB01 | Heating and boilers | HB-010 | Quarterly | N | 2026-10-26 | Open
T0043 | S03 | S03-AC10 | Air conditioning | AC-013 | Quarterly | N | 2026-10-27 | Completed | 2026-10-24
T0063 | S04 | S04-FA09 | Fire alarm | FA-010 | Weekly | Y | 2026-10-08 | Completed | 2026-10-04
T0072 | S04 | S04-HB04 | Heating and boilers | HB-002 | Annual | N | 2026-10-12 | Completed | 2026-10-11
T0073 | S04 | S04-EL09 | Emergency lighting | EL-011 | Monthly | Y | 2026-10-12 | Completed | 2026-10-09
T0055 | S04 | S04-HB06 | Heating and boilers | HB-003 | Quarterly | N | 2026-10-13 | Completed | 2026-10-11
T0058 | S04 | S04-AC05 | Air conditioning | AC-014 | Quarterly | N | 2026-10-13 | Completed | 2026-10-09
T0060 | S04 | S04-FA08 | Fire alarm | FA-010 | Quarterly | Y | 2026-10-13 | Completed | 2026-10-11
T0062 | S04 | S04-HB12 | Heating and boilers | HB-011 | Quarterly | N | 2026-10-15 | No access |  | Keyholder not present
T0070 | S04 | S04-DS11 | Doors and shutters | DS-019 | Six-monthly | N | 2026-10-15 | Completed | 2026-10-12
T0056 | S04 | S04-HB08 | Heating and boilers | HB-017 | Quarterly | N | 2026-10-18 | Completed | 2026-10-16
T0064 | S04 | S04-DS05 | Doors and shutters | DS-010 | Six-monthly | N | 2026-10-19 | Completed | 2026-10-17
T0065 | S04 | S04-AC09 | Air conditioning | AC-010 | Quarterly | N | 2026-10-22 | No access |  | Room in use, client refused access
T0068 | S04 | S04-WH11 | Water hygiene | WH-002 | Quarterly | Y | 2026-10-23 | Completed | 2026-10-19
T0059 | S04 | S04-EL02 | Emergency lighting | EL-005 | Monthly | Y | 2026-10-24 | Completed | 2026-10-29
T0067 | S04 | S04-WH03 | Water hygiene | WH-015 | Monthly | Y | 2026-10-24 | Completed | 2026-10-22
T0061 | S04 | S04-AC07 | Air conditioning | AC-017 | Six-monthly | N | 2026-10-26 | Completed | 2026-10-23
T0069 | S04 | S04-DS06 | Doors and shutters | DS-019 | Six-monthly | N | 2026-10-27 | Completed | 2026-10-27
T0057 | S04 | S04-AC03 | Air conditioning | AC-008 | Quarterly | N | 2026-10-30 | Completed | 2026-10-27
T0071 | S04 | S04-DS06 | Doors and shutters | DS-020 | Six-monthly | N | 2026-10-30 | Completed | 2026-10-27
T0066 | S04 | S04-WH04 | Water hygiene | WH-008 | Monthly | Y | 2026-10-31 | Completed | 2026-10-27
T0085 | S05 | S05-FA05 | Fire alarm | FA-004 | Quarterly | Y | 2026-10-01 | Completed | 2026-10-01
T0086 | S05 | S05-DS09 | Doors and shutters | DS-015 | Six-monthly | N | 2026-10-01 | Completed | 2026-10-01
T0081 | S05 | S05-FA12 | Fire alarm | FA-005 | Quarterly | Y | 2026-10-02 | Completed | 2026-10-01
T0080 | S05 | S05-HB10 | Heating and boilers | HB-019 | Quarterly | N | 2026-10-03 | Completed | 2026-10-02
T0077 | S05 | S05-WH06 | Water hygiene | WH-015 | Monthly | Y | 2026-10-06 | Completed | 2026-10-05
T0074 | S05 | S05-DS11 | Doors and shutters | DS-018 | Six-monthly | N | 2026-10-08 | Completed | 2026-10-05
T0083 | S05 | S05-EL03 | Emergency lighting | EL-015 | Monthly | Y | 2026-10-09 | Completed | 2026-10-09
T0084 | S05 | S05-FA08 | Fire alarm | FA-008 | Weekly | Y | 2026-10-10 | Completed | 2026-10-10
T0089 | S05 | S05-HB09 | Heating and boilers | HB-007 | Quarterly | N | 2026-10-11 | Completed | 2026-10-09
T0076 | S05 | S05-DS05 | Doors and shutters | DS-004 | Six-monthly | N | 2026-10-14 | Completed | 2026-10-14
T0087 | S05 | S05-DS04 | Doors and shutters | DS-019 | Six-monthly | N | 2026-10-20 | Completed | 2026-10-17
T0078 | S05 | S05-AC03 | Air conditioning | AC-001 | Six-monthly | N | 2026-10-26 | Completed | 2026-10-22
T0079 | S05 | S05-DS08 | Doors and shutters | DS-006 | Six-monthly | N | 2026-10-26 | Completed | 2026-10-25
T0090 | S05 | S05-HB03 | Heating and boilers | HB-020 | Quarterly | N | 2026-10-27 | Completed | 2026-10-27
T0088 | S05 | S05-DS06 | Doors and shutters | DS-020 | Six-monthly | N | 2026-10-28 | Completed | 2026-10-25
T0082 | S05 | S05-HB06 | Heating and boilers | HB-017 | Quarterly | N | 2026-10-29 | Open
T0075 | S05 | S05-WH09 | Water hygiene | WH-003 | Monthly | Y | 2026-10-30 | Completed | 2026-10-29
T0097 | S06 | S06-HB01 | Heating and boilers | HB-006 | Annual | N | 2026-10-01 | Completed | 2026-10-01
T0093 | S06 | S06-DS01 | Doors and shutters | DS-001 | Six-monthly | N | 2026-10-04 | Completed | 2026-10-01
T0091 | S06 | S06-FA01 | Fire alarm | FA-004 | Weekly | Y | 2026-10-09 | Completed | 2026-10-07
T0092 | S06 | S06-AC09 | Air conditioning | AC-002 | Six-monthly | N | 2026-10-09 | Completed | 2026-10-08
T0099 | S06 | S06-AC08 | Air conditioning | AC-002 | Quarterly | N | 2026-10-14 | Completed | 2026-10-13
T0102 | S06 | S06-EL12 | Emergency lighting | EL-005 | Monthly | Y | 2026-10-14 | Completed | 2026-10-14
T0095 | S06 | S06-EL05 | Emergency lighting | EL-009 | Monthly | Y | 2026-10-16 | Completed | 2026-10-15
T0104 | S06 | S06-EL05 | Emergency lighting | EL-019 | Monthly | Y | 2026-10-17 | Completed | 2026-10-13
T0105 | S06 | S06-HB11 | Heating and boilers | HB-003 | Quarterly | N | 2026-10-18 | Completed | 2026-10-18
T0103 | S06 | S06-AC04 | Air conditioning | AC-014 | Six-monthly | N | 2026-10-19 | Completed | 2026-10-18
T0094 | S06 | S06-EL05 | Emergency lighting | EL-006 | Monthly | Y | 2026-10-20 | Completed | 2026-10-20
T0100 | S06 | S06-HB08 | Heating and boilers | HB-002 | Quarterly | N | 2026-10-21 | Completed | 2026-10-17
T0096 | S06 | S06-EL05 | Emergency lighting | EL-013 | Monthly | Y | 2026-10-24 | Completed | 2026-10-21
T0101 | S06 | S06-FA06 | Fire alarm | FA-016 | Weekly | Y | 2026-10-27 | Completed | 2026-10-24
T0098 | S06 | S06-EL02 | Emergency lighting | EL-014 | Monthly | Y | 2026-10-29 | Completed | 2026-10-25
Note on A1: Sample rows are fictional. Delete them and paste your own export (columns A to K).
Note on L1: Formula. On time / Late / No access / Carried over / Out of period.

## Sites
site_id | site_name | region
S01 | Halden Court Offices | North
S02 | Brookmere Medical Centre | Midlands
S03 | Corran Street Depot | North
S04 | Ashwell Primary School | South East
S05 | Pellow Retail Unit 7 | South East
S06 | Fenmoor Library | Midlands
Note on A1: Sample sites are fictional. Replace with your own site register.

## Settings
Setting | Value | Notes
Period start | 2026-10-01 | First day of the reporting period
Period end | 2026-10-31 | Last day of the reporting period
Tolerance (days after due date) | 0 | 0 means the due date is already the end of the permitted window
Green threshold (adjusted compliance) | 95% | At or above this is Green (example value)
Amber threshold (adjusted compliance) | 85% | At or above this, but below Green, is Amber (example value)
Sample data in this workbook is fictional.